## Sheet1
Details | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15
Planning | bar: week 1
Requirement Specification | bar: week 2
UI/UX Design | bar: week 3
Prototype Design | bar: week 4
Frontend and Backend setup | bar: week 5
Authentication and User Roles | bar: week 6
Marketplace Development | bar: week 8
Payment Methods | bar: week 11
Search, Filter | bar: week 11
Community Forum | bar: week 6 to week 7
Testing and Debugging | bar: week 12
Launch and Deployment | bar: week 15
|  | Kamrul |  | Kibria |  | Combined